## Readme
lo | 2018-10-17
Authors | Rafael Gomez, Jessica Gonzalez, Elijah Marchese, Lino Valdovinos, Katherine Way
Emails | rgome020@ucr.edu, jgonz117@ucr.edu, emarc004@ucr.edu, lgonz041@ucr.edu, kway001@ucr.edu
Description | Speech to ASL is an android app that allows the user to translate his words to ASL(American sign language). The user can write a sentence or speak a sentence to the app. The app will then play a series of videos translating the words in ASL.
Tabs | Notes
"Product Backlog" | As a user, I want to be able to use my voice as input (3hrs)
As a user, I want to see what word/letter is being translated at any given momen (4hrs)
as user, I want an image per letter of the word not in the database (3hrs)
As a user, I to be able to input text rather than through voice (3.5hrs)
As a user, I want to see that my input is correct. (2hrs)
As a user, I want accurate data used for the translations. (4hrs)
As a user, I want videos played word by word from my phrase (2.5hrs)
"Task Board" | To Do (Sprint Backlog)
Speech to Text
Display text from speech
Highlight the words
Display each letter in word
Just input text to ASL
Extract data from database
Parse phrases inputed from voice and text
"Archives" | In progress
"Burndown Chart" | in progress

## Burndown chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
1 | 33 | 14 | 0 | 33 | 33
2 | 35 | 0 | 0 | 19 | 26.25
3 | 36 | 0 | 0 | 19 | 21.875
4 | 36 | 0 | 0 | 19 | 17.5
5 | 36 | 0 | 0 | 19 | 13.125
6 | 34 | 0 | 0 | 19 | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0
9 |  |  |  |  | -4.375

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Speech to Text | As a user, I want to be able to use my voice as input | 6 | 1
2 | Highlight the words | As a user, I want to see what word/letter is being translated at any given momen | 3 | 5
3 | Display each letter in word | as user, I want an image per letter of the word not in the database | 7 | 1
4 | Just input text to ASL | As a user, I to be able to input text rather than through voice | 6 | 2 | To be split
5 | Display text from speech | As a user, I want to see that my input is correct. | 2 | 1
6 | Extract video data from website | As a user, I want accurate data used for the translations. | 7 | 3
7 | Parse phrases form speech to text and text input | As a user, I want videos played word by word from my phrase | 2 | 1
33

## TaskBoard
To Do (Sprint Backlog) | In Progress | Testing | Done
Speech to Text
Display text from speech
Highlight the words (Eli)
Display each letter in word(Rafael)
Just input text to ASL
Extract video data from website (Jess)
Parse phrases inputed from voice and text(Kat)

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Lino Valdovinos | Task 1: Speech to Text,Display text from speech,Just input text to ASL
1 | Rafael Gomez | Task ?
1 | Jessica Gonzalez | Task ?
1 | Elijah Marchese | Task ?
1 | Katherine Way | Task ?