## Readme
lo | 2018-10-17
Authors | Rafael Gomez, Jessica Gonzalez, Elijah Marchese, Lino Valdovinos, Katherine Way
Emails | rgome020@ucr.edu, jgonz117@ucr.edu, emarc004@ucr.edu, lgonz041@ucr.edu, kway001@ucr.edu
Description | Speech to ASL is an android app that allows the user to translate his words to ASL(American sign language). The user can write a sentence or speak a sentence to the app. The app will then play a series of videos translating the words in ASL.
Tabs | Notes
"Product Backlog" | As a user, I want to be able to use my voice as input (3hrs)
As a user, I want to see what word/letter is being translated at any given momen (4hrs)
as user, I want an image per letter of the word not in the database (3hrs)
As a user, I to be able to input text rather than through voice (3.5hrs)
As a user, I want to see that my input is correct. (2hrs)
As a user, I want accurate data used for the translations. (4hrs)
As a user, I want videos played word by word from my phrase (2.5hrs)
"Task Board" | To Do (Sprint Backlog)
Save favorite phrases
Have a history of phrases
Clear phrase option
Factoring
Pause and Stop sequence
Play Selected Word
Create Menu
"Archives" | In progress
"Burndown Chart" | in progress

## Burndown chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
1 | 33 | 14 | 0 | 33 | 33
2 | 35 | 0 | 0 | 19 | 26.25
3 | 36 | 0 | 0 | 19 | 21.875
4 | 36 | 0 | 0 | 19 | 17.5
5 | 36 | 0 | 0 | 19 | 13.125
6 | 34 | 0 | 0 | 19 | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0
9 |  |  |  |  | -4.375

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Speech to Text | As a user, I want to be able to use my voice as input | 6 | 1
2 | Highlight the words | As a user, I want to see what word/letter is being translated at any given momen | 3 | 5
3 | Display each letter in word | as user, I want an image per letter of the word not in the database | 7 | 1
4 | Just input text to ASL | As a user, I to be able to input text rather than through voice | 6 | 2 | To be split
5 | Display text from speech | As a user, I want to see that my input is correct. | 2 | 1
6 | Extract video data from website | As a user, I want accurate data used for the translations. | 7 | 3
7 | Parse phrases form speech to text and text input | As a user, I want videos played word by word from my phrase | 2 | 1
8 | Save favorite phrases | As a user, I want to save phrases that I frequently use | 8 | 2
9 | Have a history of phrases | As a user, I want to see all phrases that I have previously searched | 6 | 2
10 | Clear phrase option | As a user, I want to be able to clear what I have spoken or written to input something new | 2 | 4
11 | Factoring
12 | Pause and Stop sequence | As a user, I want to be able to stop on a certain word rather than playing the next one | 4 | 4
13 | Play Selected Word | As a user, I want to select a word from the phrase to repeat its translation | 5 | 3
14 | Create Menu | As a user, I want to have a menu to navigate through the app | 9 | 2
67

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Lino Valdovinos | Task 1,4,5: Speech to Text,Display text from speech,Just input text to ASL
1 | Rafael Gomez | Task 3 : Display images of each word
1 | Jessica Gonzalez | Task 6: Extract video data from website
1 | Elijah Marchese | Task ?
1 | Katherine Way | Task ?

## TaskBoard
To Do (Sprint Backlog) | In Progress | Testing | Done
Speech to Text
Display text from speech
Display each letter in word
Just input text to ASL
Extract video data from website
Highlight the words (Eli)
Parse phrases inputed from voice and text(Kat)
Embed videos (Lino)
Save favorite phrases(Rafael)
Have a history of phrases (Jess?)
Clear phrase option (Kat)
Factoring (Lino)
Pause and Stop sequence
Play Selected Word
Create a menu (Jess)